## Daily Planning
Date | Odoo ID | Site | Task Description | Priority | Assigned Tech | planned Date | Estimated Hours | Required Parts/Tools | Status | Technician note
2026-02-19 | T2596 | Workshop | Eureka | Normal | Abu Baker | 2026-02-22 | 1 |  | Done
2026-02-21 | T2607 | Workshop | Fellow ODE 1 | Normal | Abu Baker | 2026-02-22 | 0.75 |  | Done
2026-02-18 | T2584 | Workshop | Kalerm B5 | Normal | Abu Baker | 2026-02-22 | 0.75 |  | Done
2026-02-18 | T2580 | Workshop | Kalerm A5 | Normal | Abu Baker | 2026-02-22 | 0.75 |  | Done
2026-02-20 | T2598 | Workshop | Kalerm B5 | Normal | Abu Baker | 2026-02-22 | 0.75 |  | Done
2026-02-21 | T2604 | Workshop | Kalerm B3-2 | Normal | Abu Baker | 2026-02-22 | 0.75 |  | Done
2026-02-21 | T2606 | Workshop | Kalerm B5 | Normal | Abu Baker | 2026-02-22 | 0.75 |  | Done
2026-02-21 | T2610 | Workshop | Kalerm B5 | Normal | Abu Baker | 2026-02-22 | 0.75 |  | Done |  |  | Done
2026-02-21 | T2609 | Workshop | Wacaco PIXA | Normal | Robin | 2026-02-22 | 0.75 |  | Done |  |  | Pending
2026-02-21 | T2611 | Client Site | Electricity | High | Robin | 2026-02-22 | 3 |  | Done |  |  | Pending
2026-02-04 | T2493 | Workshop | Melanger | Normal | Robin | 2026-02-22 | 1 |  | Done
2026-02-21 | T2616 | Client Site | KvdW Spirit | High | Walid | 2026-02-22 | 3 |  | Done |  |  | Pending
2026-02-21 | T2530 | 48E Site | Training | High | Walid | 2026-02-22 | 2 |  | Done |  |  | Done
2026-02-21 | T2606 | Workshop | Kalerm B5 | Normal | Abu Baker | 2026-02-23 | 0.75 |  | Done
2026-02-21 | T2610 | Workshop | Kalerm B5 | Normal | Abu Baker | 2026-02-23 | 0.75 |  | Done
2026-02-22 | T2617 | Workshop | Kalerm | Normal | Abu Baker | 2026-02-23 | 0.75 |  | Done |  |  | Done
2026-02-22 | T2620 | Workshop | Kalerm | Normal | Abu Baker | 2026-02-23 | 0.75 |  | Done |  |  | Done
2026-02-22 | T2621 | Workshop | Kalerm | Normal | Abu Baker | 2026-02-23 | 0.75 |  | Done |  |  | Done
2026-02-19 | T2592 | Workshop | ECM | Normal | Abu Baker | 2026-02-23 | 1.5 |  | Done
2026-02-18 | T2590 | Client Site | Giesen | Normal | Robin, Abu Baker | 2026-02-23 | 3 |  | Done |  |  | Done
2026-02-22 | T2619 | Workshop | Baratza | Normal | Robin | 2026-02-23 | 1.5 |  | Done |  |  | Done
2026-02-21 | T2622 | Client Site | KvdW Spirit | High | Robin | 2026-02-23 | 4 |  | Done |  |  | Done
2026-02-11 | T2530 | Client Site | Site inspection | Normal | Walid | 2026-02-23 | 1 |  | Done |  |  | Done
2026-02-22 | T2615 | Client Site | Site inspection | Normal | Walid | 2026-02-23 | 1 |  | Done |  |  | Done
2026-02-22 | T2624 | Client Site | Eureka | Normal | Walid | 2026-02-23 | 1 |  | Done |  |  | Done
2026-02-22 | T2618 | 48E Site | AC | Normal | Walid | 2026-02-23 | 0.25 |  | Done |  |  | Done
2026-02-23 | T2633 | Client Site | Kalerm Y | Normal | Walid | 2026-02-23 | 1.5 |  | Done |  |  | Done
2026-02-21 | T2610 | Workshop | Kalerm B5 | Normal | Abu Baker | 2026-02-24 | 0.75 |  | Done
2026-02-22 | T2617 | Workshop | Kalerm | Normal | Abu Baker | 2026-02-24 | 0.75 |  | Done
2026-02-22 | T2620 | Workshop | Kalerm | Normal | Abu Baker | 2026-02-24 | 0.75 |  | Done
2026-02-22 | T2621 | Workshop | Kalerm | Normal | Abu Baker | 2026-02-24 | 0.75 |  | Done
2026-02-23 | T2623 | Workshop | Kalerm | Normal | Abu Baker | 2026-02-24 | 0.75 |  | Done
2026-02-22 | T2619 | Workshop | Baratza | Normal | Robin | 2026-02-24 | 1.5 |  | Done
2026-02-23 | T2634 | Workshop | ECM | High | Robin | 2026-02-24 | 2 |  | Done
2026-02-23 | T2626 | Workshop | Fellow ODE | Normal | Robin | 2026-02-24 | 1 |  | Done
2026-02-23 | T2625 | Workshop | Fellow Aiden | Normal | Robin | 2026-02-24 | 1 |  | Warranty
2026-02-23 | T2628 | Workshop | Eureka Helios | Normal | Robin | 2026-02-24 | 1 |  | Done
2026-02-24 | T2635 | Client Site | KvdW | High | Walid | 2026-02-24 | 3 |  | Done
2026-02-21 | T2614 | Client Site | Giesen | High | Walid | 2026-02-24 | 3 |  | Done
2026-02-23 | T2631 | Workshop | Kalerm | Normal | Abu Baker | 2026-02-25 | 0.75 |  | Done
2026-02-23 | T2634 | Workshop | ECM | High | Abu Baker | 2026-02-25 | 3 |  | Done
2026-02-24 | T2637 | Workshop | Kalerm | Normal | Abu Baker | 2026-02-25 | 0.75 |  | Done
2026-02-24 | T2638 | Workshop | Baratza | Normal | Abu Baker | 2026-02-25 | 0.5 |  | Done
2026-02-24 | T2639 | Workshop | Fellow | Normal | Abu Baker | 2026-02-25 | 0.5 |  | Done
2026-02-16 | T2565 | Workshop | Baratza | Normal | Robin | 2026-02-25 | 1 |  | Done
2026-02-18 | T2586 | Workshop | Baratza | Normal | Robin | 2026-02-25 | 1 |  | Done
2026-02-16 | T2569 | Workshop | Baratza | Normal | Robin | 2026-02-25 | 1 |  | Done
2026-02-15 | T2555 | Workshop | Baratza | Normal | Robin | 2026-02-25 | 1 |  | Done
2026-02-16 | T2566 | Workshop | Baratza | Normal | Robin | 2026-02-25 | 1 |  | Done
2026-02-16 | T2567 | Workshop | Baratza | Normal | Robin | 2026-02-25 | 1 |  | Done
2026-02-25 | T2648 | Client Site | Eureka | Normal | Walid | 2026-02-25 | 0.75 |  | Done
2026-02-25 | T2647 | Client Site | Weber EG-1 | Normal | Walid | 2026-02-25 | 1 |  | Done
2026-02-25 | T2649 | Client Site | Caye | Normal | Walid | 2026-02-25 | 0.5 |  | Done
2026-02-25 | T2650 | Client Site | Weber EG-1 | Normal | Walid | 2026-02-25 | 1 |  | Done
2026-02-25 | T2651 | Client Site | Weber EG-1 | Normal | Walid | 2026-02-25 | 1 |  | Done
2026-02-24 | T2641 | Workshop | ECM | Normal | Robin | 2026-02-26 | 1.5 |  | Done
2026-02-23 | T2632 | Workshop | ECM | Normal | Robin | 2026-02-26 | 1.5 |  | Done
2026-02-23 | T2627 | Workshop | Baratza | Normal | Robin | 2026-02-26 | 1 |  | Done
2026-02-26 | T2657 | 48E Site | Cooler | Normal | Robin | 2026-02-26 | 1 |  | Done
2026-02-24 | T2642 | Workshop | Baratza | Normal | Robin | 2026-02-26 | 1 |  | Waiting spare parts
2026-02-25 | T2644 | Workshop | Kalerm | Normal | Abu Baker | 2026-02-26 | 1 |  | Done
2026-02-25 | T2646 | Workshop | Kalerm | Normal | Abu Baker | 2026-02-26 | 1 |  | Done
2026-02-26 | T2658 | 48E Site | Caye | Normal | Walid | 2026-02-26 | 1 |  | Done
2026-02-25 | T2653 | Workshop | Kalerm | Normal | Abu Baker | 2026-02-28 | 1 |  | Done
2026-02-26 | T2663 | Workshop | Kalerm | Normal | Abu Baker | 2026-02-28 | 1 |  | Done
2026-02-26 | T2656 | Workshop | Fellow | Normal | Robin | 2026-02-28 | 1.5 |  | Done
2026-02-07 | T2508 | Workshop | Baratza | Normal | Robin | 2026-02-28 | 1 |  | Done
2026-02-27 | T2664 | Client Site | 3TEMP | Normal | Walid | 2026-02-28 | 1 |  | Done
2026-02-27 | T2665 | Client Site | IB7 | Normal | Walid | 2026-02-28 | 1.5 |  | Done
2026-02-25 | T2646 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-01 | 1 |  | Done
2026-02-25 | T2654 | Workshop | Ovo | Normal | Abu Baker | 2026-03-01 | 1 |  | Done
2026-02-26 | T2661 | Workshop | ECM | Normal | Abu Baker | 2026-03-01 | 2 |  | Done
2026-02-26 | T2662 | Workshop | La Pavoni | Normal | Abu Baker | 2026-03-01 | 1 |  | Done
2026-02-26 | T2659 | Workshop | Baratza | Normal | Robin | 2026-03-01 | 1 |  | Waiting spare parts
2026-02-26 | T2660 | Workshop | Baratza | Normal | Robin | 2026-03-01 | 1 |  | Done
2026-02-28 | T2667 | 48E Site | Filling machine | Normal | Robin | 2026-03-01 | 1 |  | Done
2026-02-28 | T2669 | 48E Site | cabinet | Normal | Robin | 2026-03-01 | 0.5 |  | Done
2026-02-28 | T2671 | Client Site | IB7 | Normal | Robin | 2026-03-01 | 2 |  | Done
2026-03-01 | T2677 | Client Site | KvdW | Normal | Robin, Walid | 2026-03-01 | 2.5 |  | Done
2026-02-28 | T2668 | Workshop | Mazzer | Normal | Abu Baker | 2026-03-02 | 1 |  | Done
2026-03-01 | T2672 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-02 | 1 |  | Done
2026-03-01 | T2673 | Workshop | Baratza | Normal | Abu Baker | 2026-03-02 | 0.5 |  | Done
2026-03-01 | T2674 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-02 | 1 |  | Done
2026-03-01 | T2678 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-02 | 1 |  | Done
2026-03-01 | T2679 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-02 | 1 |  | Done
2026-03-01 | T2676 | Workshop | Eureka | Normal | Robin | 2026-03-02 | 1 |  | Done
2026-03-01 | T2675 | Workshop | Fellow | Normal | Robin | 2026-03-02 | 1 |  | Done
2026-02-28 | T2671 | Client Site | IB7 | Normal | Robin | 2026-03-02 | 2 |  | Done
2026-02-28 | T2669 | 48E Site | cabinet | Normal | Robin | 2026-03-02 | 0.5 |  | Done
2026-03-02 | T2683 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-03 | 1 |  | Done
2026-03-02 | T2682 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-03 | 1 |  | Done
2026-03-02 | T2681 | Workshop | Eureka | Normal | Abu Baker | 2026-03-03 | 1 |  | Done
2026-03-03 | T2684 | 48E Site | Giesen | Normal | Robin, Abu Baker | 2026-03-03 | 3 |  | Done
2026-03-03 | T2685 | 48E Site | Giesen | Normal | Robin, Abu Baker | 2026-03-03 | 3 |  | Done
2026-03-03 | T2686 | 48E Site | Iberital | Normal | Robin | 2026-03-03 | 1 |  | Done
2026-02-28 | T2669 | 48E Site | cabinet | Normal | Robin | 2026-03-03 | 0.5 |  | Done
2026-03-03 | T2688 | Client Site | FloSmart | Normal | Walid, Robin | 2026-03-03 | 1.5 |  | Done
2026-03-03 | T2687 | Client Site | ECM | Normal | Walid | 2026-03-03 | 2 |  | Done
2026-02-24 | T2636 | Client Site | Lelit Bianca | Normal | Walid | 2026-03-03 | 1 |  | Done
2026-03-03 | T2687 | Client Site | ECM | Normal | Abu Baker | 2026-03-04 | 3 |  | Done
2026-03-02 | T2683 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-04 | 1 |  | Done
2026-03-02 | T2682 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-04 | 1 |  | Done
2026-03-02 | T2681 | Workshop | Eureka | Normal | Abu Baker | 2026-03-04 | 1 |  | Done
2026-03-03 | T2689 | Workshop | Fellow Aiden | Normal | Robin | 2026-03-04 | 1 |  | Warranty
2026-03-03 | T2690 | Workshop | Baratza Encor | Normal | Robin | 2026-03-04 | 0.5 |  | Done
2026-03-03 | T2691 | Workshop | Eureka Pro | Normal | Robin | 2026-03-04 | 1 |  | Done
2026-03-03 | T2692 | Workshop | Eureka Pro | Normal | Robin | 2026-03-04 | 1 |  | Done
2026-03-03 | T2693 | Workshop | Baratza Forte | Normal | Robin | 2026-03-04 | 1 |  | Done
2026-02-24 | T2636 | Client Site | Lelit Bianca | Normal | Walid | 2026-03-04 | 1 |  | Done
2026-03-04 | T2703 | Client Site | Caye | Normal | Walid | 2026-03-04 | 2 |  | Done
2026-03-04 | T2704 | Client Site | KvdW | Normal | Walid | 2026-03-04 | 2 |  | Done
2026-03-03 | T2687 | Workshop | ECM | Normal | Abu Baker | 2026-03-05 | 3 |  | Done
2026-03-03 | T2697 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-05 | 1 |  | Done
2026-03-03 | T2696 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-05 | 1 |  | Done
2026-03-03 | T2695 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-05 | 1 |  | Done
2026-03-05 | T2705 | 48E Site | Electricity | High | Robin | 2026-03-05 | 3 |  | Done
2026-03-03 | T2689 | Workshop | Fellow Aiden | High | Robin | 2026-03-05 | 1 |  | Warranty
2026-03-03 | T2690 | Workshop | Baratza Encor | Normal | Robin | 2026-03-05 | 0.5 |  | Done
2026-03-03 | T2691 | Workshop | Eureka Pro | Normal | Robin | 2026-03-05 | 1 |  | Done
2026-03-03 | T2692 | Workshop | Eureka Pro | Normal | Robin | 2026-03-05 | 1 |  | Done
2026-03-03 | T2693 | Workshop | Baratza Forte | Normal | Robin | 2026-03-05 | 1 |  | Done
2026-03-04 | T2701 | Client Site | ECM | Normal | Walid | 2026-03-05 | 2 |  | Done
2026-03-04 | T2700 | Workshop | ECM | Normal | Abu Baker | 2026-03-07 | 3 |  | Done
2026-02-05 | T2706 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-07 | 1 |  | Done
2026-03-06 | T2710 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-07 | 1 |  | Done
2026-03-05 | T2708 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-07 | 1 |  | Done
2026-03-06 | T2711 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-07 | 1 |  | Done
2026-03-05 | T2690 | Workshop | Baratza | Normal | Abu Baker | 2026-03-07 | 0.5 |  | Done
2026-03-03 | T2689 | Workshop | Fellow Aiden | Normal | Robin | 2026-03-07 | 1 |  | Warranty
2026-03-03 | T2694 | Workshop | Fellow EKG | Normal | Robin | 2026-03-07 | 1 |  | Done
2026-03-03 | T2692 | Workshop | Eureka Pro | Normal | Robin | 2026-03-07 | 1 |  | Done
2026-03-04 | T2702 | Workshop | Eureka Pro | Normal | Robin | 2026-03-07 | 1 |  | Done
2026-03-04 | T2699 | Workshop | Acaia | Normal | Robin | 2026-03-07 | 1 |  | Done
2026-02-23 | T2629 | Workshop | Phoenix scale | Normal | Robin | 2026-03-07 | 0.5 |  | Pending
2026-03-03 | T2693 | Workshop | Baratza Forte | Normal | Robin | 2026-03-07 | 1 |  | Done
2026-03-04 | T2701 | Client Site | ECM | Normal | Walid | 2026-03-07 | 1.5 |  | Done
2026-03-07 | T2713 | Client Site | KvdW | Normal | Walid | 2026-03-07 | 2 |  | Done
2026-03-07 | T2723 | 48E Site | Training center | Normal | Walid | 2026-03-07 | 1 |  | Done
2026-03-03 | T2687 | Workshop | ECM | High | Abu Baker | 2026-03-08 | 3 |  | Done
2026-03-07 | T2712 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-08 | 1 |  | Done
2026-03-07 | T2726 | Workshop | Arrange | Normal | Robin, Abu Baker | 2026-03-08 | 2 |  | Done
2026-03-03 | T2686 | 48E Site | Iberital | High | Robin | 2026-03-08 | 1 |  | Done
2026-03-07 | T2714 | Workshop | Kalerm | Normal | Robin | 2026-03-08 | 1 |  | Done
2026-03-07 | T2715 | Workshop | Fellow ODE | Normal | Robin | 2026-03-08 | 0.5 |  | Done
2026-03-07 | T2716 | Workshop | Kalerm | Normal | Robin | 2026-03-08 | 1 |  | Done
2026-03-07 | T2724 | 48E Site | Wall | Normal | Walid | 2026-03-08 | 1 |  | Done
2026-03-05 | T2707 | 48E Site | Chair legs | Normal | Walid | 2026-03-08 | 0.25 |  | Done
2026-03-08 | T2727 | 48E Site | chair screws | Normal | Walid | 2026-03-08 | 1 |  | Done
2026-03-06 | T2709 | Client Site | Iberital Tandem | Normal | Walid | 2026-03-09 | 1.5 |  | Done
2026-03-07 | T2718 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-09 | 1 |  | Done
2026-03-07 | T2725 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-09 | 1 |  | Done
2026-03-07 | T2725 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-09 | 1 |  | Done
2026-03-07 | T2721 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-09 | 1 |  | Done
2026-03-08 | T2730 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-09 | 1 |  | Done
2026-03-08 | T2731 | Workshop | Baratza Encor | Normal | Abu Baker | 2026-03-09 | 1 |  | Done
2026-03-07 | T2716 | Workshop | Kalerm | Normal | Robin | 2026-03-09 | 1 |  | Done
2026-03-07 | T2717 | Workshop | ECM | Normal | Robin | 2026-03-09 | 2 |  | Done
2026-03-07 | T2719 | Workshop | Baratza forte | Normal | Robin | 2026-03-09 | 1 |  | Done
2026-03-07 | T2722 | Workshop | ECM | Normal | Robin | 2026-03-09 | 3 |  | Done
2026-03-08 | T2732 | 48E Site | QuinSpin | High | Robin | 2026-03-09 | 1 |  | Done
2026-03-08 | T2738 | 48E Site | Bakery | Normal | Walid | 2026-03-09 | 2 |  | Done
2026-03-08 | T2733 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-10 | 1 |  | Done
2026-03-09 | T2742 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-10 | 1 |  | Done
2026-03-09 | T2741 | Workshop | Fellow | Normal | Abu Baker | 2026-03-10 | 1 |  | Done
2026-03-10 | T2759 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-11 | 1 |  | Done
2026-03-10 | T2750 | Workshop | Fellow ODE | Normal | Abu Baker | 2026-03-11 | 1 |  | Done
2026-03-10 | T2745 | Workshop | Fellow ODE | Normal | Abu Baker | 2026-03-11 | 1 |  | Done
2026-03-10 | T2759 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-11 | 1 |  | Done
2026-03-07 | T2717 | Workshop | ECM | Normal | Robin | 2026-03-11 | 1 |  | Done
2026-03-10 | T2757 | 48E Site | Electricity | Normal | Robin | 2026-03-11 | 6 |  | Done
2026-03-11 | T2773 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-12 | 1 |  | Done
2026-03-11 | T2763 | Workshop | Fellow ODE | Normal | Abu Baker | 2026-03-12 | 1 |  | Done
2026-03-10 | T2758 | Workshop | ECM | Normal | Abu Baker | 2026-03-12 | 3 |  | Done
2026-03-11 | T2766 | Workshop | Fellow ODE | Normal | Abu Baker | 2026-03-12 | 1 |  | Done
2026-03-11 | T2764 | Workshop | Fellow ODE | Normal | Abu Baker | 2026-03-12 | 1 |  | Done
2026-03-11 | T2765 | Workshop | Fellow ODE | Normal | Abu Baker | 2026-03-12 | 1 |  | Warranty
2026-03-08 | T2728 | Workshop | ECM | Normal | Abu Baker | 2026-03-12 | 1 |  | Done
2026-02-23 | T2627 | Workshop | Baratza | Normal | Robin | 2026-03-12 | 1 |  | Done
2026-03-12 | T2776 | Workshop | Eureka Helios | Normal | Robin | 2026-03-12 | 1 |  | Done
2026-02-24 | T2640 | Workshop | Baratza Forte | Normal | Robin | 2026-03-12 | 1 |  | Done
2026-03-10 | T2760 | Workshop | ECM | Normal | Robin | 2026-03-12 | 1.5 |  | Done
2026-03-07 | T2722 | Workshop | ECM | Normal | Robin | 2026-03-12 | 2 |  | Done
2026-03-08 | T2739 | Workshop | ECM | Normal | Robin | 2026-03-12 | 1 |  | Done
2026-03-12 | T2779 | 48E Site | Fellow EKG | Normal | Robin | 2026-03-14 | 1 |  | Done
2026-03-10 | T2757 | 48E Site | Electricity | High | Robin | 2026-03-14 | 6 |  | Done
2026-03-11 | T2772 | Workshop | Scale | Normal | Robin | 2026-03-14 | 0.5 |  | Warranty
2026-03-11 | T2771 | Workshop | WDT | Normal | Robin | 2026-03-14 | 0.5 |  | Done
2026-03-08 | T2734 | Workshop | Baratza Forte | Normal | Robin | 2026-03-14 | 1 |  | Done
2026-03-08 | T2735 | Workshop | Baratza Forte | Normal | Robin | 2026-03-14 | 1 |  | Done
2026-03-08 | T2736 | Workshop | Baratza Forte | Normal | Robin | 2026-03-14 | 1 |  | Waiting spare parts
2026-03-08 | T2737 | Workshop | Baratza Forte | Normal | Robin | 2026-03-14 | 0.25 |  | Done
2026-03-09 | T2744 | Workshop | Baratza Forte | Normal | Robin | 2026-03-14 | 1 |  | Done
2026-03-10 | T2761 | Workshop | Flojet | Normal | Robin | 2026-03-14 | 0.5 |  | Done
2026-03-09 | T2743 | Workshop | Baratza Forte | Normal | Robin | 2026-03-14 | 0.5 |  | Done
2026-03-10 | T2746 | Workshop | IB7 | Normal | Abu Baker | 2026-03-14 | 2 |  | Done
2026-03-10 | T2747 | Workshop | IB7 | Normal | Abu Baker | 2026-03-14 | 2 |  | Done
2026-03-10 | T2751 | Workshop | Eureka | Normal | Abu Baker | 2026-03-14 | 1 |  | Done
2026-03-10 | T2752 | Workshop | Eureka | Normal | Abu Baker | 2026-03-14 | 1 |  | Done
2026-03-12 | T2777 | Client Site | Kalerm Y | Normal | Walid | 2026-03-14 | 1.5 |  | Done
2026-03-13 | T2782 | Workshop | ECM | Normal | Walid | 2026-03-14 | 0.5 |  | Done
2026-03-11 | T2767 | Client Site | Site inspection | Normal | Walid | 2026-03-14 | 1.5 |  | Done
2026-03-12 | T2779 | 48E Site | Fellow EKG | Normal | Robin | 2026-03-15 | 1 |  | Done
2026-03-10 | T2757 | 48E Site | Electricity | High | Robin | 2026-03-15 | 6 |  | Done
2026-03-17 | T2796 | 48E Site | Bakery | Normal | Robin | 2026-03-15 | 1 |  | Done
2026-03-17 | T2797 | 48E Site | Bakery | Normal | Robin | 2026-03-15 | 1 |  | Done
2026-03-10 | T2748 | Workshop | IB7 | Normal | Abu Baker | 2026-03-15 | 2 |  | Done
2026-03-10 | T2749 | Workshop | IB7 | Normal | Abu Baker | 2026-03-15 | 2 |  | Done
2026-03-10 | T2753 | Workshop | Eureka | Normal | Abu Baker | 2026-03-15 | 1 |  | Done
2026-03-10 | T2754 | Workshop | Eureka | Normal | Abu Baker | 2026-03-15 | 1 |  | Done
2026-03-15 | T2788 | Client Site | Giesen | Normal | Walid | 2026-03-15 | 2 |  | Done
2026-03-12 | T2777 | Client Site | Kalerm Y | Normal | Walid | 2026-03-15 | 1.5 |  | Done
2026-03-17 | T2801 | Workshop | KvdW | High | Robin | 2026-03-16 | 6 |  | Done
2026-03-14 | T2784 | Workshop | Fellow | Normal | Robin | 2026-03-16 | 0.5 |  | Done
2026-03-17 | T2799 | 48E Site | Bakery | High | Robin, Abu Baker | 2026-03-16 | 1 |  | Done
2026-03-17 | T2798 | 48E Site | Bakery | High | Robin, Abu Baker | 2026-03-16 | 1 |  | Done
2026-03-13 | T2781 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-16 | 1 |  | Done
2026-03-17 | T2795 | Client Site | 3Temp | Normal | Walid | 2026-03-16 | 1 |  | Done
2026-03-17 | T2794 | 48E Site | Coded | Normal | Walid | 2026-03-16 | 1.5 |  | Done
2026-03-17 | T2800 | 48E Site | bakery | High | Robin | 2026-03-17 | 2 |  | Done
2026-03-17 | T2801 | Workshop | KvdW | High | Robin | 2026-03-17 | 3 |  | Done
2026-03-12 | T2778 | Workshop | ECM | High | Abu Baker | 2026-03-17 | 3 |  | Done
2026-03-12 | T2775 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-17 | 1 |  | Done
2026-03-15 | T2787 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-17 | 1 |  | Done
2026-03-17 | T2810 | Workshop | Fellow OPUS | Normal | Abu Baker | 2026-03-18 | 0.5 |  | Done
2026-03-17 | T2811 | Workshop | Fellow Aiden | Normal | Abu Baker | 2026-03-18 | 1 |  | Done
2026-01-14 | T2345 | Workshop | Eureka SD | Normal | Abu Baker | 2026-03-18 | 0.5 |  | Done
2026-03-11 | T2762 | Workshop | Baratza forte | Normal | Abu Baker | 2026-03-18 | 1 |  | Done
2026-03-18 | T2815 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-19 | 1 |  | Done
2026-03-11 | T2770 | Workshop | Baratza forte | Normal | Abu Baker | 2026-03-19 | 1 |  | Done
2026-03-19 | T2820 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-19 | 1 |  | Done
2026-02-18 | T2585 | Workshop | Baratza forte | Normal | Robin | 2026-03-19 | 1 |  | Done
2026-03-23 | T2834 | 48E Site | Giesen | High | Abu Baker | 2026-03-22 | 3 |  | Done
2026-02-23 | T2835 | 48E Site | Giesen | High | Robin | 2026-03-22 | 3 |  | Done
2026-03-19 | T2819 | 48E Site | QuinSpin | Normal | Robin | 2026-03-22 | 1 |  | Done
2026-03-16 | T2791 | 48E Site | water hose | Normal | Walid | 2026-03-23 | 0.25 |  | Done
2026-03-17 | T2809 | 48E Site | water hose | Normal | Walid | 2026-03-23 | 0.25 |  | Done
2026-03-16 | T2792 | Workshop | Fellow EKG | Normal | Robin | 2026-03-23 | 0.5 |  | Warranty
2026-03-23 | T2832 | 48E Site | Giesen | Normal | Robin | 2026-02-23 | 0.25 |  | Done
2026-03-23 | T2833 | Client Site | FloSmart | Normal | Robin | 2026-03-23 | 2 |  | Done
2026-03-20 | T2825 | Workshop | Eureka Pro | Normal | Abu Baker | 2026-03-23 | 1 |  | Done
2026-03-21 | T2827 | Workshop | La pavoni | Normal | Abu Baker | 2026-02-23 | 1 |  | Done
2026-03-22 | T2828 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-23 | 1 |  | Done
2026-03-22 | T2830 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-23 | 1 |  | Done
2026-03-22 | T2831 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-23 | 1 |  | Done
2026-03-19 | T2821 | 48E Site | Ice Maker | Normal | Robin | 2026-03-24 | 1 |  | Done
2026-03-16 | T2793 | 48E Site | Acaia | Normal | Robin | 2026-03-24 | 1 |  | Done
2026-03-14 | T2785 | Workshop | Baratza forte | Normal | Robin | 2026-03-24 | 1 |  | Done
2026-03-16 | T2789 | Workshop | Baratza forte | Normal | Robin | 2026-03-24 | 1 |  | Done
2026-03-18 | T2818 | Client Site | Giesen | Normal | Robin | 2026-03-24 | 2 |  | Done
2026-03-23 | T2836 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-24 | 1 |  | Done
2026-03-23 | T2837 | Workshop | kalerm | Normal | Abu Baker | 2026-03-24 | 1 |  | Done
2026-03-08 | T2737 | Workshop | Baratza forte | Normal | Abu Baker | 2026-03-24 | 1 |  | Done
2026-03-19 | T2816 | Workshop | Baratza forte | Normal | Abu Baker | 2026-03-24 | 1 |  | Done
2026-03-19 | T2817 | Workshop | Baratza forte | Normal | Abu Baker | 2026-03-24 | 1 |  | Done
2026-03-18 | T2813 | Client Site | Giesen W6 Pro | Normal | Walid | 2026-03-24 | 3 |  | Done
2026-03-24 | T2838 | Client Site | Kalerm M50 | Normal | Robin | 2026-03-25 | 6 |  | Done
2026-03-28 | T2866 | Client Site | Giesen | Normal | Robin | 2026-03-25 | 2 |  | Done
2026-03-25 | T2849 | Client Site | Giesen | Normal | Robin | 2026-03-25 | 2 |  | Done
2026-03-24 | T2840 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-25 | 1 |  | Done
2026-03-19 | T2817 | Workshop | Baratza forte | Normal | Abu Baker | 2026-03-25 | 1 |  | Done
2026-03-24 | T2842 | Workshop | kalerm | Normal | Abu Baker | 2026-03-25 | 1 |  | Done
2026-03-24 | T2844 | Workshop | kalerm | Normal | Abu Baker | 2026-03-25 | 1 |  | Done
2026-03-24 | T2843 | Workshop | Eureka SD | Normal | Abu Baker | 2026-03-25 | 1 |  | Done
2026-03-19 | T2818 | Workshop | Baratza forte | Normal | Abu Baker | 2026-03-25 | 1 |  | Done
2026-03-25 | T2845 | Client Site | Giesen W15 | High | Walid | 2026-03-25 | 2 |  | Done
2026-03-28 | T2864 | Client Site | Giesen W60 | High | Walid | 2026-03-25 | 6 |  | Done
2026-03-25 | T2851 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-26 | 1 |  | Done
2026-03-25 | T2846 | Workshop | kalerm | Normal | Abu Baker | 2026-03-26 | 1 |  | Done
2026-03-25 | T2848 | Workshop | kalerm | Normal | Abu Baker | 2026-03-26 | 1 |  | Done
2026-03-25 | T2852 | Workshop | Eureka SD | Normal | Abu Baker | 2026-03-26 | 1 |  | Done
2026-03-28 | T2865 | Client Site | Giesen W30 | High | Walid, Robin | 2026-03-26 | 4 |  | Done
2026-03-28 | T2864 | Client Site | Giesen W60 | High | Walid, Robin | 2026-03-26 | 4 |  | Done
2026-03-28 | T2870 | Client Site | Giesen W6 | Normal | Robin, Abu Baker | 2026-03-28 | 3 |  | Done
2026-03-28 | T2871 | Client Site | Giesen W6 | Normal | Robin, Abu Baker | 2026-03-28 | 3 |  | Done
2026-03-28 | T2872 | 48E Site | Giesen W15 | Normal | Robin | 2026-03-28 | 1 |  | Done
2026-03-28 | T2873 | 48E Site | Sealer device | Normal | Robin | 2026-03-28 | 1 |  | Done | 1 hour, please run the device when it needed to get more Life span of the part
2026-03-28 | T2879 | 48E Site | Glass | Normal | Robin | 2026-03-29 | 1 |  | Done | 30 min took measurements
2026-03-19 | T2821 | 48E Site | Ice Maker | Normal | Robin | 2026-03-29 | 1 |  | Done | 15 min
2026-03-16 | T2793 | 48E Site | Acaia | Normal | Robin | 2026-03-29 | 1 |  | Pending
2026-03-28 | T2876 | Client Site | Giesen | Normal | Robin | 2026-03-29 | 1 |  | Done | start: 02: 15. end 03:00 45 min
2026-03-11 | T2774 | Workshop | Baratza forte | Normal | Robin | 2026-03-29 | 1 |  | Done | 1 hour . replaced grinder unit
2026-03-16 | T2789 | Workshop | Baratza forte | Normal | Robin | 2026-03-29 | 1 |  | Done | 1.5 hour 12 : 30 - 2 00
2026-03-28 | T2875 | Client Site | KvdW SlimJim | Normal | Robin | 2026-03-29 | 2 |  | Done | 03 : 00 to 04: 45 1 and 45 min
2026-03-28 | T2863 | Workshop | Baratza Encor | Normal | Abu Baker | 2026-03-29 | 1 |  | Planned | From 4:33-4:53
2026-03-24 | T2839 | Workshop | Fellow OPUS | Normal | Abu Baker | 2026-03-29 | 1 |  | Warranty | From 11:16-11:26
2026-03-25 | T2847 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-29 | 1 |  | Done | Yesterday done 3:15 - 4:05
2026-03-26 | T2853 | Workshop | Baratza forte | Normal | Abu Baker | 2026-03-29 | 1 |  | In progress | From 11:45-12:45
2026-03-26 | T2854 | Workshop | Baratza forte | Normal | Abu Baker | 2026-03-29 | 1 |  | In progress | From 12:45-1:45
2026-03-26 | T2855 | Workshop | Fellow EKG | Normal | Abu Baker | 2026-03-29 | 1 |  | Planned | From 12:55 - 1:07
2026-03-26 | T2856 | Workshop | Eureka ATOM | Normal | Abu Baker | 2026-03-29 | 1 |  | Planned | Start at 1:28 | Done at 2:00
2026-03-26 | T2858 | Workshop | Fellow ODE | Normal | Abu Baker | 2026-03-29 | 1 |  | Planned | Start 2:09 | Done at 2:30
2026-03-28 | T2880 | Client Site | Slayer | Normal | Walid | 2026-03-29 | 3 |  | Planned
2026-03-29 | T2881 | Client Site | FloJet | Normal | Walid | 2026-03-29 | 1.5 |  | Planned
2026-03-28 | T2878 | Client Site | Giesen | Normal | Robin, Abu Baker | 2026-03-30 | 3 |  | Planned
2026-03-21 | T2827 | Workshop | La pavoni | Normal | Robin | 2026-03-30 | 1 |  | Planned
2026-03-20 | T2825 | Workshop | Eureka Pro | Normal | Robin | 2026-03-30 | 1 |  | Planned
2026-02-18 | T2585 | Workshop | Baratza forte | Normal | Robin | 2026-03-30 | 1 |  | Planned
2026-03-25 | T2850 | Client Site | Kalerm Y | Normal | Robin | 2026-03-30 | 1 |  | Planned
2026-03-28 | T2877 | Workshop | ECM | Normal | Abu Baker | 2026-03-30 | 3 |  | Planned
2026-03-26 | T2859 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-30 | 1 |  | Planned
2026-03-27 | T2860 | Workshop | Fellow Aiden | Normal | Robin | 2026-03-31 | 1 |  | Planned
2026-03-27 | T2861 | Workshop | Fellow ODE | Normal | Robin | 2026-03-31 | 1 |  | Planned
2026-03-28 | T2868 | Workshop | ECM | Normal | Robin | 2026-03-31 | 2 |  | Planned
2026-03-28 | T2869 | Workshop | Gaggia Academia | Normal | Robin | 2026-03-31 | 2 |  | Planned
2026-03-28 | T2867 | Client Site | Giesen | Normal | Abu Baker, Walid | 2026-03-31 | 3 |  | Planned
2026-03-27 | T2862 | Workshop | Breville grinder | Normal | Abu Baker | 2026-03-31 | 1 |  | Planned
2026-03-28 | T2874 | Workshop | Kalerm | Normal | Abu Baker | 2026-03-31 | 1 |  | Planned
2026-03-16 | T2808 | Client Site | KvdW | Normal | Robin | 2026-04-01 | 3 |  | Planned
2026-03-16 | T2807 | Client Site | KvdW | Normal | Robin | 2026-04-01 | 3 |  | Planned
2026-03-16 | T2806 | Client Site | Weber | Normal | Robin | 2026-04-02 | 2 |  | Planned
2026-03-16 | T2804 | Client Site | Weber | Normal | Robin | 2026-04-02 | 2 |  | Planned
2026-10-26 | T2178 | Workshop | Outdoor chair | High | Robin | 2026-04-04 | 3 |  | Planned
-

## Work Log
Date | Technician | Job ID | Start Time | End Time | Actual Hours | Work Done | Status | Issues / Notes
2026-02-22 | Abu Baker | T2596 | 9:00 | 10:00 | 1 |  | Done
2026-02-22 | Abu Baker | T2607 | 10:00 | 11:00 | 0.75 |  | Done
2026-02-22 | Abu Baker | T2584 | 11:00 | 12:00 | 0.75 |  | Done
2026-02-22 | Abu Baker | T2580 | 12:00 | 13:00 | 0.75 |  | Done
2026-02-22 | Abu Baker | T2604 | 13:00 | 14:00 | 0.75 |  | Done
2026-02-22 | Abu Baker | T2606 |  |  |  |  | Pending
2026-02-22 | Abu Baker | T2610 |  |  |  |  | Pending
2026-02-22 | Robin | T2611 | 10:00 | 13:00 | 3 |  | Done
2026-02-22 | Robin | T2609 | 13:00 | 14:00 | 1 |  | Done
2026-02-22 | Robin | T2493 | 14:00 | 15:00 | 1 |  | Done
2026-02-22 | Walid | T2530 | 13:00 | 15:00 | 2 |  | Done
2026-02-22 | Walid | T2530 | 19:00 | 21:00 | 2 |  | Done
2026-02-23 | Robin, Abu Baker | T2590 | 9:00 | 11:30 | 2.5 |  | Done
2026-02-23 | Abu Baker | T2606 | 12:00 | 13:00 | 1 |  | Done
2026-02-23 | Abu Baker | T2610 |  |  |  |  | Pending
2026-02-23 | Abu Baker | T2617 |  |  |  |  | Pending
2026-02-23 | Abu Baker | T2620 |  |  |  |  | Pending
2026-02-23 | Abu Baker | T2621 |  |  |  |  | Pending
2026-02-23 | Abu Baker | T2592 | 13:00 | 14:30 | 1.5 |  | Done
2026-02-23 | Robin | T2619 |  |  |  |  | Pending
2026-02-23 | Robin | T2622 | 20:00 | 0:30 | 4.5 |  | Done
2026-02-23 | Walid | T2530 | 20:30 | 20:45 | 0.25 |  | Done
2026-02-23 | Walid | T2615 | 21:00 | 22:00 | 1 |  | Done
2026-02-23 | Walid | T2624 | 19:00 | 7:30 | 0.5 |  | Done
2026-02-23 | Walid | T2618 | 10:00 | 10:15 | 0.25 |  | Done
2026-02-23 | Walid | T2633 | 10:45 | 0:15 | 1.5 |  | Done
2026-02-24 | Abu Baker | T2610 | 10:00 | 11:00 | 1 |  | Done
2026-02-24 | Abu Baker | T2617 | 9:00 | 10:00 | 1 |  | Done
2026-02-24 | Abu Baker | T2620 | 11:00 | 11:45 | 0.75 |  | Done
2026-02-24 | Abu Baker | T2621 | 12:00 | 13:45 | 1.75 |  | Done
2026-02-24 | Abu Baker | T2623 | 14:00 | 15:00 | 1 |  | Done
2026-02-24 | Robin | T2619 | 9:00 | 9:30 | 0.5 |  | Done
2026-02-24 | Robin | T2634 | 9:30 | 11:30 | 2 |  | Pending
2026-02-24 | Robin | T2626 | 11:30 | 12:00 | 0.5 |  | Pending | warranty claim
2026-02-24 | Robin | T2625 | 12:00 | 12:45 | 0.75 |  | Pending | warranty claim
2026-02-24 | Robin | T2628 | 13:00 | 1:45 | 0.75 |  | Done
2026-02-24 | Walid | T2635 | 19:00 | 21:30 | 2.5 |  | Done
2026-02-24 | Walid | T2614 | 22:00 | 0:30 | 2.5 |  | Done
2026-02-25 | Abu Baker | T2631 | 10:00 | 10:15 | 0.25 |  | Done
2026-02-25 | Abu Baker | T2634 | 10:15 | 13:00 | 2.75 |  | Done
2026-02-25 | Abu Baker | T2637 | 13:00 | 14:00 | 1 |  | Done
2026-02-25 | Abu Baker | T2638 | 14:00 | 2:35 | 0.5 |  | Done
2026-02-25 | Abu Baker | T2639 | 2:35 | 3:05 | 0.5 |  | Done
2026-02-25 | Robin | T2565 | 9:00 | 10:00 | 1 |  | Done
2026-02-25 | Robin | T2586 | 10:00 | 11:00 | 1 |  | Done
2026-02-25 | Robin | T2569 | 11:00 | 11:30 | 0.5 |  | Done
2026-02-25 | Robin | T2555 | 11:30 | 12:15 | 0.75 |  | Done
2026-02-25 | Robin | T2566 | 14:00 | 15:00 | 1 |  | Done
2026-02-25 | Robin | T2567 | 12:15 | 12:45 | 0.5 |  | Done
2026-02-25 | Walid | T2648 | 19:00 | 20:00 | 1 |  | Done
2026-02-25 | Walid | T2647 | 20:15 | 21:00 | 0.75 |  | Done
2026-02-25 | Walid | T2649 | 21:15 | 22:00 | 0.75 |  | Done
2026-02-25 | Walid | T2650 | 22:15 | 23:00 | 0.75 |  | Done
2026-02-25 | Walid | T2651 | 23:15 | 0:00 | 0.75 |  | Done
2026-02-26 | Robin | T2641 | 10:20 | 11:50 | 1.5 |  | Done
2026-02-26 | Robin | T2632 | 12:00 | 13:30 | 1.5 |  | Done
2026-02-26 | Robin | T2627 | 13:30 | 14:00 | 0.5 |  | Done
2026-02-26 | Robin | T2657 | 14:00 | 2:45 | 0.75 |  | Done
2026-02-26 | Robin | T2642 | 14:45 | 3:15 | 0.5 |  | Pending
2026-02-26 | Abu Baker | T2644 | 10:00 | 11:00 | 1 |  | Done
2026-02-26 | Abu Baker | T2646 | 11:00 | 12:30 | 1.5 |  | Done
2026-02-26 | Walid | T2658 | 12:00 | 20:00 | 8 |  | Done
2026-02-28 | Abu Baker | T2653 | 11:00 | 12:00 | 1 |  | Done
2026-02-28 | Abu Baker | T2663 | 12:00 | 1:30 | 1.5 |  | Done
2026-02-28 | Robin | T2656 | 11:00 | 13:00 | 2 |  | Done
2026-02-28 | Robin | T2508 | 13:00 | 14:00 | 1 |  | Done
2026-02-28 | Walid | T2664 | 19:00 | 20:00 | 1 |  | Done
2026-02-28 | Walid | T2665 | 20:30 | 22:00 | 1.5 |  | Done
2026-03-01 | Abu Baker | T2646 | 11:00 | 11:30 | 0.5 |  | Done
2026-03-01 | Abu Baker | T2654 | 13:30 | 14:00 | 0.5 |  | Done
2026-03-01 | Abu Baker | T2661 | 11:30 | 13:30 | 2 |  | Done
2026-03-01 | Abu Baker | T2662 | 14:00 | 15:00 | 1 |  | Done
2026-03-01 | Robin | T2659 | 11:00 | 11:45 | 0.75 |  | Done
2026-03-01 | Robin | T2660 | 12:00 | 13:00 | 1 |  | Done
2026-03-01 | Robin | T2667 | 14:00 | 2:30 | 0.5 |  | Done
2026-03-01 | Robin | T2669 |  |  |  |  | Pending
2026-03-01 | Robin | T2671 |  |  |  |  | Pending
2026-03-01 | Walid, Robin | T2677 | 19:00 | 21:30 | 2.5 |  | Done
2026-03-02 | Abu Baker | T2668 | 10:00 | 10:45 | 0.75 |  | Done
2026-03-02 | Abu Baker | T2672 | 11:00 | 12:30 | 1.5 |  | Done
2026-03-02 | Abu Baker | T2673 | 12:30 | 13:15 | 0.75 |  | Done
2026-03-02 | Abu Baker | T2674 | 13:15 | 14:00 | 0.75 |  | Done
2026-03-02 | Abu Baker | T2678 | 14:00 | 2:45 | 0.75 |  | Done
2026-03-02 | Abu Baker | T2679 | 14:45 | 15:30 | 0.75 |  | Done
2026-03-02 | Robin | T2676 | 10:00 | 10:30 | 0.5 |  | Done
2026-03-02 | Robin | T2675 |  |  |  |  | Pending
2026-03-02 | Robin | T2671 | 12:30 | 14:30 | 2 |  | Done
2026-03-02 | Robin | T2669 |  |  |  |  | Pending
2026-03-03 | Abu Baker | T2683 |  |  |  |  | Pending
2026-03-03 | Abu Baker | T2682 |  |  |  |  | Pending
2026-03-03 | Abu Baker | T2681 |  |  |  |  | Pending
2026-03-03 | Robin, Abu Baker | T2684 | 6:00 | 9:00 | 3 |  | Done
2026-03-03 | Robin, Abu Baker | T2685 | 9:00 | 12:00 | 3 |  | Done
2026-03-03 | Robin | T2686 |  |  |  |  | Pending
2026-03-03 | Robin | T2669 | 12:00 | 12:45 | 0.75 |  | Done
2026-03-03 | Walid | T2688 | 10:00 | 13:00 | 3 |  | Done
2026-03-03 | Walid | T2687 | 21:00 | 22:00 | 1 |  | Pending
2026-03-03 | Walid | T2636 | 19:00 | 20:30 | 1.5 |  | Pending
2026-03-04 | Abu Baker | T2687 |  |  |  |  | Pending
2026-03-04 | Abu Baker | T2683 | 11:00 | 12:00 | 1 |  | Done
2026-03-04 | Abu Baker | T2682 | 13:00 | 14:00 | 1 |  | Done
2026-03-04 | Abu Baker | T2681 | 12:00 | 13:00 | 1 |  | Done
2026-03-04 | Robin | T2689 |  |  |  |  | Pending | Sick leave
2026-03-04 | Robin | T2690 |  |  |  |  | Pending | Sick leave
2026-03-04 | Robin | T2691 |  |  |  |  | Pending | Sick leave
2026-03-04 | Robin | T2692 |  |  |  |  | Pending | Sick leave
2026-03-04 | Robin | T2693 |  |  |  |  | Pending | Sick leave
2026-03-04 | Walid | T2636 | 19:00 | 21:00 | 2 |  | Done
2026-03-04 | Walid | T2703 | 21:00 | 23:00 | 2 |  | Done
2026-03-04 | Walid | T2704 | 23:00 | 1:00 | 2 |  | Done
2026-03-05 | Abu Baker | T2687 |  |  |  |  | Pending
2026-03-05 | Abu Baker | T2697 | 11:00 | 12:00 | 1 |  | Done
2026-03-05 | Abu Baker | T2696 | 10:00 | 11:00 | 1 |  | Done
2026-03-05 | Abu Baker | T2695 | 12:00 | 12:30 | 0.5 |  | Done
2026-03-05 | Robin | T2705 | 9:00 | 14:00 | 5 |  | Done
2026-03-05 | Robin | T2689 |  |  |  |  | Pending
2026-03-05 | Robin | T2690 |  |  |  |  | Pending
2026-03-05 | Robin | T2691 |  |  |  |  | Pending
2026-03-05 | Robin | T2692 |  |  |  |  | Pending
2026-03-05 | Robin | T2693 |  |  |  |  | Pending
2026-03-05 | Walid | T2701 | 19:00 | 20:00 | 1 |  | Pending
2026-03-07 | Abu Baker | T2700 | 9:00 | 11:00 | 2 |  | Pending
2026-03-07 | Abu Baker | T2706 | 11:00 | 12:00 | 1 |  | Done
2026-03-07 | Abu Baker | T2710 | 12:00 | 13:00 | 1 |  | Done
2026-03-07 | Abu Baker | T2708 | 13:00 | 14:00 | 1 |  | Done
2026-03-07 | Abu Baker | T2711 | 14:00 | 15:00 | 1 |  | Done
2026-03-07 | Abu Baker | T2690 | 15:00 | 16:00 | 1 |  | Done
2026-03-07 | Robin | T2689 | 9:00 | 10:00 | 1 |  | Done
2026-03-07 | Robin | T2694 | 10:00 | 23:00 | 1 |  | Done
2026-03-07 | Robin | T2692 | 11:00 | 12:00 | 1 |  | Done
2026-03-07 | Robin | T2702 | 12:00 | 13:00 | 1 |  | Done
2026-03-07 | Robin | T2699 | 13:00 | 14:00 | 1 |  | Done
2026-03-07 | Robin | T2629 | 14:00 | 15:00 | 1 |  | Done
2026-03-07 | Robin | T2693 | 15:00 | 16:00 | 1 |  | Done
2026-03-07 | Walid | T2701 | 19:00 | 8:30 | 1.5 |  | Done
2026-03-07 | Walid | T2713 | 21:00 | 23:00 | 2 |  | Done
2026-03-07 | Walid | T2723 | 23:00 | 0:00 | 1 |  | Done
2026-03-08 | Abu Baker | T2687 | 12:00 | 15:00 | 3 |  | Done
2026-03-08 | Abu Baker | T2712 | 9:00 | 10:00 | 1 |  | Done
2026-03-08 | Abu Baker | T2700 | 10:00 | 12:00 | 2 |  | Done
2026-03-08 | Abu Baker | T2720 | 12:00 | 13:00 | 1 |  | Done
2026-03-08 | Robin, Abu Baker | T2726 | 13:00 | 14:00 | 1 |  | Done
2026-03-08 | Robin | T2686 | 17:00 | 18:30 | 1.5 |  | Done
2026-03-08 | Robin | T2714 | 11:00 | 12:00 | 1 |  | Done
2026-03-08 | Robin | T2715 | 12:00 | 12:30 | 0.5 |  | Done
2026-03-08 | Robin | T2716 |  |  |  |  | Pending
2026-03-08 | Walid | T2724 | 8:00 | 9:30 | 1.5 |  | Done
2026-03-08 | Walid | T2707 | 19:00 | 7:05 | 0.25 |  | Done
2026-03-08 | Walid | T2727 | 8:00 | 9:00 | 1 |  | Done
2026-03-09 | Walid | T2709 | 0:00 | 1:30 | 1.5 |  | Done
2026-03-09 | Abu Baker | T2718 | 9:00 | 10:00 | 1 |  | Done
2026-03-09 | Abu Baker | T2725 | 10:00 | 10:15 | 0.25 |  | Done
2026-03-09 | Abu Baker | T2721 | 10:20 | 12:20 | 2 |  | Done
2026-03-09 | Abu Baker | T2730 | 12:30 | 13:30 | 1 |  | Done
2026-03-09 | Abu Baker | T2731 | 13:30 | 14:00 | 0.5 |  | Done
2026-03-09 | Robin | T2716 | 9:00 | 10:00 | 1 |  | Done
2026-03-09 | Robin | T2717 | 10:00 | 12:00 | 2 |  | Pending
2026-03-09 | Robin | T2719 | 12:00 | 13:00 | 1 |  | Done
2026-03-09 | Robin | T2722 | 13:00 | 15:00 | 2 |  | Pending
2026-03-09 | Robin | T2732 | 9:00 | 10:00 | 1 |  | Done
2026-03-09 | Walid | T2738 | 11:00 | 14:00 | 3 |  | Done
2026-03-10 | Abu Baker | T2733 | 12:00 | 13:00 | 1 |  | Done
2026-03-10 | Abu Baker | T2742 | 13:00 | 14:00 | 1 |  | Done
2026-03-10 | Abu Baker | T2741 | 14:00 | 14:30 | 0.5 |  | Done
2026-03-11 | Abu Baker | T2759 | 10:00 | 12:30 | 2.5 |  | Done
2026-03-11 | Abu Baker | T2750 | 14:30 | 15:00 | 0.5 |  | Done
2026-03-11 | Abu Baker | T2745 | 9:00 | 10:00 | 1 |  | Done
2026-03-11 | Abu Baker | T2759 | 10:00 | 11:00 | 1 |  | Done
2026-03-11 | Robin | T2717 | 9:00 | 11:00 | 2 |  | Done
2026-03-11 | Robin | T2757 | 9:00 | 15:00 | 6 |  | Pending
2026-03-12 | Abu Baker | T2773 | 9:00 | 10:00 | 1 |  | Done
2026-03-12 | Abu Baker | T2763 | 10:00 | 10:30 | 0.5 |  | Done
2026-03-12 | Abu Baker | T2758 | 10:30 | 13:00 | 2.5 |  | Done
2026-03-12 | Abu Baker | T2766 | 13:00 | 13:30 | 0.5 |  | Done
2026-03-12 | Abu Baker | T2764 | 13:30 | 14:00 | 0.5 |  | Done
2026-03-12 | Abu Baker | T2765 | 14:00 | 14:30 | 0.5 |  | Done
2026-03-12 | Abu Baker | T2728 | 14:30 | 15:00 | 0.5 |  | Done
2026-03-12 | Robin | T2627 | 9:00 | 9:45 | 0.75 |  | Done
2026-03-12 | Robin | T2776 | 10:15 | 10:45 | 0.5 |  | Done
2026-03-12 | Robin | T2640 | 9:45 | 10:15 | 0.5 |  | Done
2026-03-12 | Robin | T2760 | 10:45 | 11:00 | 0.75 |  | Done
2026-03-12 | Robin | T2722 | 11:00 | 13:00 | 2 |  | Done
2026-03-12 | Robin | T2739 | 13:00 | 14:00 | 1 |  | Pending
2026-03-14 | Robin | T2739 | 10:00 | 10:45 | 0.75 |  | Done
2026-03-14 | Robin | T2772 | 10:45 | 11:00 | 0.25 |  | Done | Warranty claim
2026-03-14 | Robin | T2771 | 11:00 | 11:15 | 0.25 |  | Done
2026-03-14 | Robin | T2734 | 11:15 | 12:00 | 0.75 |  | Done
2026-03-14 | Robin | T2735 | 12:00 | 12:45 | 0.75 |  | Done
2026-03-14 | Robin | T2736 | 12:45 | 13:30 | 0.75 |  | Done
2026-03-14 | Robin | T2637 | 13:30 | 2:15 | 0.75 |  | Done
2026-03-14 | Robin | T2638 | 14:15 | 2:30 | 0.25 |  | Done
2026-03-14 | Robin | T2744 | 14:30 | 15:00 | 0.5 |  | Done
2026-03-14 | Robin | T2761 | 15:00 | 15:30 | 0.5 |  | Done
2026-03-14 | Robin | T2743 | 15:30 | 16:00 | 0.5 |  | Done
2026-03-14 | Robin | T2779 |  |  |  |  | Pending
2026-03-14 | Robin | T2757 |  |  |  |  | Pending
2026-03-14 | Abu Baker | T2746 | 10:00 | 12:00 | 2 |  | Done
2026-03-14 | Abu Baker | T2747 | 12:00 | 14:00 | 2 |  | Done
2026-03-14 | Abu Baker | T2751 | 14:00 | 15:00 | 1 |  | Done
2026-03-14 | Abu Baker | T2752 | 15:00 | 16:00 | 1 |  | Done
2026-03-14 | Walid | T2777 |  |  |  |  | Pending | client reschedule
2026-03-14 | Walid | T2782 | 21:30 | 22:00 | 0.5 |  | Done
2026-03-14 | Walid | T2767 | 19:00 | 19:30 | 1 |  | Done
2026-03-15 | Robin | T2779 |  |  |  |  | Pending
2026-03-15 | Robin | T2796 | 22:00 | 23:00 | 1 |  | Done
2026-03-15 | Robin | T2797 | 23:00 | 0:00 | 1 |  | Done
2026-03-15 | Robin | T2757 | 9:00 | 15:00 | 6 |  | Done
2026-03-15 | Abu Baker | T2748 | 9:00 | 11:00 | 2 |  | Done
2026-03-15 | Abu Baker | T2749 | 11:00 | 13:00 | 2 |  | Done
2026-03-15 | Abu Baker | T2753 | 13:00 | 14:00 | 1 |  | Done
2026-03-15 | Abu Baker | T2754 | 14:00 | 15:00 | 1 |  | Done
2026-03-15 | Walid | T2788 | 11:00 | 13:00 | 2 |  | Done
2026-03-15 | Walid | T2777 | 19:00 | 20:00 | 1 |  | Done
2026-03-16 | Robin | T2801 | 9:00 | 15:00 | 6 |  | Pending
2026-03-16 | Robin | T2784 | 13:00 | 14:00 | 1 |  | Done
2026-03-16 | Robin, Abu Baker | T2799 | 15:00 | 16:00 | 1 |  | Done
2026-03-16 | Robin, Abu Baker | T2798 | 16:00 | 17:00 | 1 |  | Done
2026-03-16 | Abu Baker | T2781 | 9:00 | 10:00 | 1 |  | Done
2026-03-16 | Walid | T2795 | 19:00 | 20:00 | 1 |  | Done
2026-03-16 | Walid | T2794 | 21:00 | 22:30 | 1.5 |  | Done
2026-03-17 | Robin | T2800 | 9:00 | 13:00 | 4 |  | Done
2026-03-17 | Robin | T2801 | 13:00 | 16:00 | 3 |  | Done
2026-03-17 | Abu Baker | T2778 | 9:00 | 11:00 | 3 |  | Done
2026-03-17 | Abu Baker | T2775 | 11:00 | 12:00 | 1 |  | Done
2026-03-17 | Abu Baker | T2787 | 12:00 | 13:00 | 1 |  | Done
2026-03-18 | Abu Baker | T2810 | 12:00 | 12:30 | 0.5 |  | Done
2026-03-18 | Abu Baker | T2811 | 12:30 | 13:15 | 0.75 |  | Done
2026-03-18 | Abu Baker | T2345 | 13:15 | 14:15 | 1 |  | Done
2026-03-18 | Abu Baker | T2762 | 14:15 | 15:15 | 1 |  | Done
2026-03-19 | Abu Baker | T2815 | 12:30 | 13:30 | 1 |  | Done
2026-03-19 | Abu Baker | T2770 | 14:00 | 16:00 | 2 |  | Done
2026-03-19 | Abu Baker | T2820 | 16:00 | 17:00 | 1 |  | Done
2026-03-19 | Robin | T2585 |  |  |  |  | Pending
2026-03-22 | Abu Baker | T2834 | 6:00 | 9:00 | 3 |  | Done
2026-03-22 | Robin | T2835 | 6:00 | 9:00 | 3 |  | Done
2026-03-22 | Robin | T2819 | 9:00 | 10:00 | 1 |  | Done
2026-03-23 | Walid | T2791 | 9:00 | 9:15 | 0.25 |  | Done
2026-03-23 | Walid | T2809 | 15:00 | 15:15 | 0.25 |  | Done
2026-03-23 | Robin | T2792 | 13:00 | 14:00 | 1 |  | Pending | Warranty
2026-02-23 | Robin | T2832 | 9:00 | 9:30 | 0.5 |  | Done
2026-03-23 | Robin | T2833 | 14:00 | 15:30 | 1.5 |  | Done
2026-03-23 | Robin | T2825 | 9:30 | 10:15 | 0.75 |  | Pending
2026-02-23 | Robin | T2827 | 10:15 | 12:15 | 2 |  | Pending
2026-03-23 | Abu Baker | T2828 | 13:00 | 14:00 | 1 |  | Done
2026-03-23 | Abu Baker | T2830 | 14:00 | 15:00 | 1 |  | Done
2026-03-23 | Abu Baker | T2831 | 15:00 | 15:45 | 0.75 |  | Done
2026-03-24 | Robin | T2821 |  |  |  |  | Pending
2026-03-24 | Robin | T2793 |  |  |  |  | Pending
2026-03-24 | Abu Baker | T2785 | 11:00 | 12:30 | 1.5 |  | Done
2026-03-24 | Robin | T2789 |  |  |  |  | Pending
2026-03-24 | Abu Baker | T2818 | 17:00 | 18:30 | 1.5 |  | Done
2026-03-24 | Abu Baker | T2836 | 12:00 | 13:00 | 1 |  | Done
2026-03-24 | Abu Baker | T2837 | 13:00 | 14:00 | 1 |  | Done
2026-03-24 | Abu Baker | T2737 | 14:00 | 15:00 | 1 |  | Done
2026-03-24 | Abu Baker | T2816 | 15:00 | 16:00 | 1 |  | Done
2026-03-24 | Abu Baker | T2817 | 16:00 | 17:00 | 1 |  | Done
2026-03-24 | Walid | T2813 | 17:00 | 20:00 | 3 |  | Done
2026-03-25 | Robin | T2838 | 9:00 | 16:00 | 7 |  | Done
2026-03-25 | Robin | T2866 | 16:00 | 17:00 | 1 |  | Done
2026-03-25 | Robin | T2849 | 18:00 | 19:00 | 1 |  | Done
2026-03-25 | Abu Baker | T2840 | 13:00 | 14:00 | 1 |  | Done
2026-03-25 | Abu Baker | T2817 | 9:00 | 10:00 | 1 |  | Done
2026-03-25 | Abu Baker | T2842 | 14:00 | 15:00 | 1 |  | Done
2026-03-25 | Abu Baker | T2844 | 15:00 | 16:00 | 1 |  | Done
2026-03-25 | Abu Baker | T2843 | 16:00 | 17:00 | 1 |  | Done
2026-03-25 | Abu Baker | T2818 | 17:00 | 6:15 | 1.25 |  | Done
2026-03-25 | Walid | T2845 | 9:00 | 11:00 | 2 |  | Done
2026-03-25 | Walid | T2864 | 12:00 | 17:00 | 5 |  | Pending
2026-03-26 | Abu Baker | T2851 | 12:00 | 12:30 | 0.5 |  | Done
2026-03-26 | Abu Baker | T2846 | 14:00 | 15:00 | 1 |  | Done
2026-03-26 | Abu Baker | T2848 | 15:00 | 16:00 | 1 |  | Done
2026-03-26 | Abu Baker | T2852 | 16:00 | 17:00 | 1 |  | Done
2026-03-26 | Walid, Robin | T2865 | 10:00 | 14:00 | 4 |  | Done
2026-03-26 | Walid, Robin | T2864 | 14:00 | 18:00 | 4 |  | Done
2026-03-28 | Robin, Abu Baker | T2870 | 12:00 | 15:00 | 3 |  | Done
2026-03-28 | Robin, Abu Baker | T2871 | 16:00 | 17:00 | 1 |  | Done
2026-03-28 | Robin | T2872 | 9:00 | 10:00 | 1 |  | Done
2026-03-28 | Robin | T2873 | 10:00 | 11:00 | 1 |  | Done

## Daily Dashboard
Daily Dashboard
Select Date (YYYY-MM-DD): | 2026-03-27
Daily Dashboard
Key KPIs |  | By Technician (Selected Date)
Jobs Planned (Selected Date) | 9 | Technician | Jobs Done | Total Hours | Hours / Job
Jobs Completed (Selected Date) | 0 | #N/A | #N/A | #N/A | 0
Completion Rate | 0% |  |  |  | 0
Total Labor Hours (Selected Date) | 0 |  |  |  | 0
Avg Hours per Completed Job | 0 |  |  |  | 0

## Weekly Dashboard
Weekly Dashboard
Week Start Date (YYYY-MM-DD):
Week End Date (YYYY-MM-DD):
Key KPIs |  | By Technician (Week)
Jobs Planned (Week) | 0 | Technician | Jobs Done | Total Hours | Hours / Job
Jobs Completed (Week) | 0 |  |  |  | 0
Completion Rate | 0 |  |  |  | 0
Total Labor Hours (Week) | 0 |  |  |  | 0
Avg Hours per Completed Job | 0 |  |  |  | 0
0
0

## Tickets Summary
Pending Tickets | New Tickets | New under process | Total under process
0 | 7 | 1 | 9
Waiting | Awaiting spare part | Reschedule | Planned for next day | Resolved Tickets
12 | 9 | 0 | 6 | 7

## Instrcutions
Purpose
Use this file to plan jobs, record time, and review performance (daily & weekly).
1) Daily Planning (Supervisor – Every Morning)
Open Daily Planning sheet.
Add one row per job:
Date, Job ID, Task, Priority, Assigned Tech, Type (Site/Workshop), Estimated Hours.
This is the plan for the day.
Rule: Every job for today must be listed here.
2) Work Log (Technicians / Supervisor – During or End of Day)
Open Work Log sheet.
For every job worked on, add one row:
Date, Technician, Job ID, Actual Hours, Work Done, Status.
Status:
Use Done for completed jobs (exact word).
Use Pending / Waiting Parts if not finished.
Rules:
Dates must be real dates.
Actual Hours must be a number (e.g., 1.5, 2).
Use Done exactly so dashboards work.
3) Daily Dashboard (Supervisor – End of Day)
Open Daily Dashboard.
Select the date at the top.
Jobs planned vs completed
Total hours
Performance by technician
Do not edit formulas.
4) Weekly Dashboard (Supervisor – End of Week)
Open Weekly Dashboard.
Select Week Start and Week End dates.
Review:
Weekly jobs planned vs completed
Total hours
Performance by technician
Do not edit formulas.
5) Golden Rules
Every job → Daily Planning
Every worked hour → Work Log
Dashboards are read-only
Review daily and weekly